## Test Results
Suite | Scenario | Input | Expected | Actual | Result | Evidence
security (security-architect) — 2026-07-09 | Overlong question rejected | `AskRequest.question` at 2001 characters. | 422 validation error (`max_length=2000` enforced). | 422 returned. | PASS | `tests/test_security.py::test_overlong_question_rejected_with_422 PASSED`
security (security-architect) — 2026-07-09 | Boundary question at exactly 2000 chars accepted | `AskRequest.question` at exactly 2000 characters. | accepted by validation (bound is inclusive), no 422. | accepted. | PASS | `tests/test_security.py::test_boundary_question_at_exactly_2000_is_accepted_by_validation PASSED`
security (security-architect) — 2026-07-09 | Empty-string question does not crash | `question=""` | clean 422 (regression test for the previously-fixed unhandled 500 — `min_length=1` + `field_validator`). | clean 422, no crash. | PASS | `tests/test_security.py::test_empty_string_question_does_not_crash PASSED`
security (security-architect) — 2026-07-09 | Whitespace-only question does not crash | `question=" "` | clean 422 (whitespace-stripping validator rejects it before it reaches the LLM call). | clean 422, no crash. | PASS | `tests/test_security.py::test_whitespace_only_question_does_not_crash PASSED`
unit/integration (test-agent) — 2026-07-09 | Backend health check | `GET /health` | 200 response confirming the FastAPI app is importable and serving. | 200 response returned. | PASS | `tests/test_smoke.py::test_health PASSED`
UX/usability + accessibility (ui-ux-designer) — 2026-07-09 | Empty state renders per spec | Load the app fresh (backend :8421, frontend :3421). | Scope statement, labeled input, `aria-live` region present, matching UX_KB.md. | Matched exactly. | PASS | Real Playwright/Chromium session, 2026-07-06 (see `PROJECT_CONTEXT.md` "Test Results — Frontend").
UX/usability + accessibility (ui-ux-designer) — 2026-07-09 | Answered state renders per spec | Ask a grid-maintenance question with a known answer in the corpus. | Correct answer text, authority badges with correct colors, filename + as-of date always paired with color, disclosure note present, neutral container. | Matched exactly (screenshot verified). | PASS | Real Playwright/Chromium session, 2026-07-06.
UX/usability + accessibility (ui-ux-designer) — 2026-07-09 | Refused state renders per spec | Ask an out-of-corpus question. | Fixed refusal sentence, scope-statement reminder, slate-tinted container, neutral info-circle icon — not red/error styling. | Matched exactly (screenshot verified). | PASS | Real Playwright/Chromium session, 2026-07-06.
UX/usability + accessibility (ui-ux-designer) — 2026-07-09 | Cross-origin request from real browser | Submit a question from the frontend origin to the backend API. | Request succeeds. | **Initially failed** — CORS error, browser-only failure mode curl testing never caught. Fixed with scoped `CORSMiddleware` (`FRONTEND_ORIGIN` env var, not wildcard). Re-verified passing after fix. | PASS (after fix, re-verified same session) | Real Playwright/Chromium session, 2026-07-06; fix committed `d4e0055`.