## MAS Roadmap
Category | Item | Status | Notes
MVP Scope | 1. Templates (genai-chatbot, agentic-workflow, rag-knowledge-base scaffolds) | Shipped | Phases 1, 3
MVP Scope | 2. Core pipeline agents, in gate order (plan-agent -> code-agent -> test-agent -> review-agent -> deploy-agent) | Shipped | Phase 1
MVP Scope | 3. /new-project skill (orchestrates full 9-gate order) | Shipped | Phase 4 (full gate order); reduced pipeline in Phase 1
MVP Scope | 4. ui-ux-designer (non-droppable for UI-bearing templates) | Shipped | Phase 4
MVP Scope | 5. solution-architect + security-architect (joint Architecture gate) | Shipped | Phase 4
MVP Scope | 6. functional-agent + industry-expert (Intake/Plan & Backlog/Architecture SMEs) | Shipped | Phase 4
MVP Scope | 7. enhance-agent + /enhance-project + /modify-feature | Shipped | Phase 5
MVP Scope | 8. release-manager (project-level) + /cut-release | Shipped | Phase 6; automated conflict resolution deferred at time of shipping, later completed
MVP Scope | 9. usage-monitor (tracking/estimation/soft-budget) | Shipped | Phase 7; auto-pause/resume deferred at time of shipping, later completed
MVP Scope | 10. /consult skill | Shipped | Phase 8 — original MVP scope (items 1-10) 100% complete
Backlog | deliverables-agent — on-demand PPTX/DOCX/XLSX export from markdown | Shipped | Shipped 2026-07-09 for per-project exports (architecture.pptx, design.docx, test-results.xlsx); Excel rollups of ROADMAP.md/FEATURES.md and this platform-level export were the remaining scope, now in progress
Backlog | Interactive HTML knowledge-base page | Shipped (standalone) | Shipped 2026-07-09, decoupled from deliverables-agent (needed none of its Office-export tooling); regeneration currently a manual step, not yet wired to a trigger
Backlog | Cloud target_env for deploy-agent | Not started | Local-only deploy proves the pipeline first; cloud auth/infra-as-code deferred as meaningfully more work
Backlog | usage-monitor auto-pause/resume | Shipped | Shipped 2026-07-09; verified with a real 3-minute one-shot CronCreate test
Backlog | release-manager automated conflict resolution | Shipped | Shipped 2026-07-09; proximity vs. semantic conflict triage, approval never automated, only classification is
Backlog | Feature flags | Designed, deferred | Designed 2026-07-09 via mas-architect (extend release-manager, prod/flags.json, opt-in per feature); deliberately not built — no release has ever needed partial rollback yet
Backlog | Multi-suite Test-gate override policy | Shipped | Shipped 2026-07-09; suites default blocking, advisory override is a recorded human decision per project
Backlog | synthetic-data-agent | Shipped | Shipped 2026-07-12; proposed 2026-07-11 (human request during little-milestones tester-account setup), mas-architect advisory review, human-approved 2026-07-12